## Summary
Deloitte Ref. | Deloitte Sub-title | Deloitte Recommendations | Impact of Recommendation | Timeframe | Crown Comments | Status
2.1 | RMS | Consider renaming the document as Crown Resorts Limited Risk Management Framework to more accurately represent its contents. Consideration should be given to developing a Risk Management Strategy document over the medium to longer term. This document would typically set out the strategic priorities for the risk function and program, including those key areas of focus to embed a more efficient and effective risk management function. This could include reference to People and Capability, Risk Culture, Risk Appetite (including corporate profiles) and Risk Reporting. | Immaterial (title of document) Moderate | Immediate Mid-Longer term | The Crown risk management framework is the totality of its people, systems, tools, documents, etc. The Risk Management Strategy (RMS) document is only a part of it, and as such referring to the document as the 'framework' would not in our opinion properly reflect the reality of risk management and the extent of the risk management structure at Crown. Already in place at department level. Updates on material changes have been provided on an ongoing basis to the Executive Risk and Compliance Committee (ERCC) and Board Committees on progress of enhancements or development of framework elements over the past 18 months. | Rejected Already in place
2.1.1 | Risk Culture | a) Accountabilities for risk culture should be reviewed in the following sections of the draft RMS: • The Executive Summary • The role of the Board in setting the desired risk culture • The role of the Risk Management Committee (RMC) in overseeing risk culture • The role of “All other Crown staff” performing their role in a manner consistent with the expected risk culture • Monitoring and reporting b) If there is no clear expression of a target risk culture or an approach to its assessment, reference to risk culture may be better expressed as a strategic priority. | Moderate | a) Immediate b) Longer term | a) Completed (also addresses part of 2.1.2 below) b) Introduction of Group-wide 'values' was just completed. Compliance and Risk KPO into all PEPs for F20. Longer term deliverable in terms of risk culture expression in the RMS was conpleted in June 2020 with the annual review. | Completed Completed
2.1.2 | Risk Management principle (RMSS3) | Consider including safety and soundness and customer service as additional principles to support an effective and meaningful risk management framework in the ongoing review of the draft RMS document. | Moderate | Immediate | Completed | Completed
2.1.3 | Risk Identification and Assessment | No Deloitte recommendations noted |  | N/A |  | -
2.1.4 | Risk Appetite | No Deloitte recommendations noted |  | N/A |  | -
2.1.4 - a | Qualitative statements | As Crown continues to develop and embed the concept of risk appetite, any updates to the qualitative statements could consider including a clearer statement of acceptable risk tolerances. | Moderate | Longer term | Will continuously review the document and consider recommendations in future iterations | Will consider at a later stage
2.1.4 - b | Quantitative metrics and triggers | No Deloitte recommendations noted |  | N/A |  | -
2.1.4 - c | Operationalisation of the risk appetite | No Deloitte recommendations noted |  | N/A |  | -
2.1.5 | Risk Management Policy | No Deloitte recommendations noted |  | N/A |  | -
2.2 | Risk Operational Model | No Deloitte recommendations noted |  | N/A |  | -
2.2.1 | Risk Governance Framework | A more meaningful way to express the above could be as follows: • Risk ownership and risk management accountability to be clearly defined to support the consideration of risk in all decision making. This supports the integration of risk identification and assessment into organisational decision making processes; • Independent oversight, challenge, reporting and monitoring of the risk culture (INSERT) risk profile, risk management framework and material (DELETE) business decisions that have the potential to impact the organisation’s risk profile. | Moderate | Immediate | Completed Crown was not agreeable to delete the word 'material'. Per ASIC Corporate Governance Report (Oct 2019), the Board should focus on material risks, therefore it was determined that we would keep the reference to material in the definition. | Completed
2.2.2 | Three lines of defence | No Deloitte recommendations noted |  | N/A |  | -
2.2.2 - a | Role of the Board | The role of the Board should include setting the desired risk culture. | Moderate | Immediate | Completed | Completed
2.2.2 - b | Role of the RMC | Consider amending the role of the RMC to also include oversight of the embedding of the Board’s desired risk culture and management of risks within risk appetite. | Moderate | Immediate | Completed | Completed
2.2.2 - c | ERCC | Consider amending the ERCC Charter to include oversight of management of risks within risk appetite and the embedding of the Board’s desired risk culture. | Moderate | In future iterations | Will address with the next review of the ERCC Charter. | Completed
2.2.2 - d | First line of defence | For clarity the First Line of Defence commentary in the graphic should be updated. PART B - Review the accountabilities of the 1LOD to reinforce that everyone has ownership of risk and should consider risk in decision making and activities. It is also recommended that the accountabilities of all staff in the 1LOD in embedding the Board's desired risk culture should be recognised. | Minor | Immediate | Completed | Completed
2.2.2 - e | Second line of defence | Amend the above to recognise that that 2LOD own the design of the Risk Management framework. PART B - This statement could be altered to state that the risk function “own and lead” not support the communication of the risk management framework | Minor | Immediate | Completed | Completed
2.3 | Reporting | No Deloitte recommendations noted |  | N/A |  | -
2.3 - a | Use of quantitative triggers for reporting | Greater clarity could be provided on the: • Reporting of risks against risk appetite; • Nature of risk aggregation and reporting; • Definition and value of triggers and their definitions to support proactive risk management, and the timely escalation where risk appetite is exceeded. It is acknowledged that the risk appetite framework including reporting has only been recently designed and that many of the concepts above may be developed over time as the program matures. | Moderate | Longer term | Already clear reporting structure defined, with reporting against risk appetite reporting triggers at every risk committee meeting. Practice has shown effective and timely reporting and escalation of matters to the satisfaction of the Board. Will consider at a later stage and in future iterations of the RMS | Will consider at a later stage
2.3 - b | Escalation of Risk Appetite Breaches | Greater clarity could be provided on the following: • How quickly after a risk event should the approving authority be informed? This could range from immediate escalation to the line manager to a longer period for the RMC and the Board. • A description of the nature of the risk event, how it happened, and what mitigating actions have been done • What lessons have been learned, additional training given or policies or processes changed to prevent a recurrence? | Minor | In future Iterations | Both in practice and as described in the RMS, risk appetite reporting has proven effective and timely, with some matters requiring immediate notification of the Board due to their magnitude (i.e. terrorism threat in February 2018 or Nine Group media allegations in July 2019 ), while others have been adequately reported at the next meeting of the relevant committee due to their less material and time sensitive nature. The Board is satisfied with the process, and the quality and timeliness of reporting and escalation. The description in the RMS document reflects actual practices and therefore is considered adequate and appropriate for the purpose. Documentation of these processes is provided in entity processes at operational level and vary depending on the nature of the events. One process will not fit all and describing all possible events and situations is not an appropriate level of information in this document. | Completed in stages
2.4 | Risk Information Systems | Efforts related to implementing risk information systems and reporting should be continued. | - | N/A | Will continue | Part of Crown's plan, in progress
Legend:
No recommendation
Recommendation accepted and implemented
Recommendation accepted - will be implemented at a later stage
Recommendation rejected at this stage. Will be reconsidered at a later stage.